## Image Assets
Unrivaled Baseball — Phase 1 Image Asset Requirements
Status: Have / Placeholder / Needed / Optional · Priority: Launch (this week) / Launch (BLOCKER, must have day-of) / Phase 2 / —
Page | Section | Slot | Subject / What to capture | Format | Dimensions (px) | Aspect | Status | Current Placeholder | Priority | Notes
Chrome | Header / Footer | Logo (full) | Unrivaled Baseball wordmark — already inline SVG in code | SVG | vector | — | Have | inline SVG in SiteHeader.astro | — | No asset file needed; baked into code.
Chrome | Header / Footer | Logo (mark only) | UB monogram for favicon + Open Graph share image | SVG / PNG | 512×512 + 1200×630 | 1:1 + 1.91:1 | Needed | — | Launch | Favicon set (16/32/180/512) + open-graph share card.
Chrome | Meta | Open Graph share image | Hero-style image with logo overlay — appears in social previews | JPEG | 1200×630 | 1.91:1 | Needed | — | Launch | One image used for all social shares of phase-1 pages.
Home | Hero | Hero background | Wide action shot — kids playing/walking on field. Focal point lower-middle. | JPEG | 2400×1600 min | 3:2 | Have | 20250629_Ripken_Volunteer-Week_AF_098.jpeg | — | Current photo is good. Focal point set to 50% 90% in CSS.
Home | About teaser (Who We Are) | Background video | Short cinematic montage — 8–15 sec loop, no sound. Muted autoplay. | MP4 (H.264) | 1920×1080 min | 16:9 | Needed | poster image only | Launch (BLOCKER) | Currently a still photo placeholder. ≤5 MB target for performance. AAC-or-no audio.
Home | About teaser (Who We Are) | Video poster image | First-frame fallback that shows before video loads / on iOS data saver | JPEG | 1920×1080 | 16:9 | Needed | — | Launch | Should match the opening frame of the background video.
Home | Pinnacle carousel | Card 1 — Ripken Nationals | Championship round at Cooperstown — bracket, trophy, or field-wide shot | JPEG | 1600×1200 | 4:3 | Have / Replace | current uses generic photo | Launch | Best replaced with a real Cooperstown / Nationals action shot.
Home | Pinnacle carousel | Card 2 — Rocker B Ranch | Byrd Family Field / Texas ranch landscape with baseball context | JPEG | 1600×1200 | 4:3 | Needed | — | Launch | Ranch wide shot or field-at-sunset would be on-brand.
Home | Pinnacle carousel | Card 3 — Cooperstown All Star Village | Cooperstown property — players, dorms, or main field | JPEG | 1600×1200 | 4:3 | Needed | — | Launch | Should reinforce the 'pilgrimage' message.
Home | Pinnacle carousel | Card 4 — Myrtle Beach Madness | Replica MLB field at Ripken Myrtle Beach with coastal feel | JPEG | 1600×1200 | 4:3 | Needed | — | Launch | Bonus if you can get ocean/palms in frame.
Home | Founding star | Cooperstown highlight card | Hero-style Cooperstown shot — same as carousel or unique close-up | JPEG | 1600×1200 | 4:3 | Needed | — | Launch | Can reuse the carousel image if needed.
Home | Venue wall | Cooperstown All Star Village | Property exterior or signature field view | JPEG | 1200×800 | 3:2 | Needed | — | Launch
Home | Venue wall | Ripken Experience Aberdeen | Aberdeen replica big-league field | JPEG | 1200×800 | 3:2 | Needed | — | Launch
Home | Venue wall | Ripken Experience Myrtle Beach | Myrtle Beach field with coastal context | JPEG | 1200×800 | 3:2 | Needed | — | Launch
Home | Venue wall | Ripken Experience Pigeon Forge | Pigeon Forge field with Smoky Mountain context | JPEG | 1200×800 | 3:2 | Needed | — | Launch
Home | Venue wall | Sports Force Parks Cedar Point | Cedar Point property — fields with theme-park backdrop | JPEG | 1200×800 | 3:2 | Needed | — | Launch
Home | Venue wall | Sports Force Parks Manteca | Manteca property exterior or fields | JPEG | 1200×800 | 3:2 | Needed | — | Launch
Home | Venue wall | Rocker B Ranch | Texas ranch identifying shot | JPEG | 1200×800 | 3:2 | Needed | — | Launch
Home | Venue wall | Baseball Factory HQ | Columbia, MD HQ exterior or training facility | JPEG | 1200×800 | 3:2 | Needed | — | Launch
Home | Voices from the Stands | Voice card 1 — Family portrait | Parent quote — family photo (parents + kid in uniform ideal) | JPEG | 1200×1200 | 1:1 | Needed | placeholder name 'Marchetti Family' | Launch | Real name + photo required. Get signed release form.
Home | Voices from the Stands | Voice card 2 — Coach portrait | Coach in environment (dugout, field) — landscape or square crop | JPEG | 1200×1200 | 1:1 | Needed | placeholder name 'Coach Davis' | Launch | Real name + photo required.
Home | Voices from the Stands | Voice card 3 — Alumni portrait | Former player — in-game shot or portrait | JPEG | 1200×1200 | 1:1 | Needed | placeholder name 'Jordan Reyes' | Launch | Real name + photo required.
Home | Partners strip | USSSA logo | Partner monochrome logo for strip | SVG / PNG | vector / 400h | — | Needed | — | Launch | Transparent PNG or SVG preferred. Single-color or original brand mark.
Home | Partners strip | Cal Ripken Sr. Foundation logo | Partner monochrome logo for strip | SVG / PNG | vector / 400h | — | Needed | — | Launch
Home | Partners strip | Easton logo | Partner monochrome logo for strip | SVG / PNG | vector / 400h | — | Needed | — | Launch
Home | Partners strip | Rawlings logo | Partner monochrome logo for strip | SVG / PNG | vector / 400h | — | Needed | — | Launch
Home | Partners strip | Marucci logo | Partner monochrome logo for strip | SVG / PNG | vector / 400h | — | Needed | — | Launch
Local | Hero | Hero background | Weekend tournament action — recognizably regional, not a stadium | JPEG | 2400×1600 min | 3:2 | Placeholder | photo-field.png | Launch | Bracket-board / parking-lot tournament feel. Mid-action.
Local | UBN Network gallery | Gallery 1 — dust and dugouts | Dugout-level moment — bench, gloves, focused player | JPEG | 1200×900 | 4:3 | Needed | — | Launch | Caption is from copy doc: 'dust and dugouts'.
Local | UBN Network gallery | Gallery 2 — walk-off win | Walk-off celebration — players running, raised hands | JPEG | 1200×900 | 4:3 | Needed | — | Launch
Local | UBN Network gallery | Gallery 3 — opening Saturday | Crowd-and-field early-morning tournament-day scene | JPEG | 1200×900 | 4:3 | Needed | — | Launch
Local | UBN Network gallery | Gallery 4 — bracket board | The printed bracket / bracket-board photo | JPEG | 1200×900 | 4:3 | Needed | — | Launch | Hard-to-fake — should be real UBN event.
Local | UBN Network gallery | Gallery 5 — trophy presentation | Award ceremony / trophy raise | JPEG | 1200×900 | 4:3 | Needed | — | Launch
Local | Our Regions | Northeast card photo | Generic action shot tagged to NE feel (or use UBN composite) | JPEG | 1200×800 | 3:2 | Optional | — | Phase 2 | Region cards currently use accent bar — photo is optional.
Local | Our Regions | Mid-Atlantic card photo | Region-flavored action shot | JPEG | 1200×800 | 3:2 | Optional | — | Phase 2
Local | Our Regions | Southeast card photo | Region-flavored action shot | JPEG | 1200×800 | 3:2 | Optional | — | Phase 2
Local | Our Regions | Midwest card photo | Region-flavored action shot | JPEG | 1200×800 | 3:2 | Optional | — | Phase 2
Local | Our Regions | Mountain West card photo | Region-flavored action shot | JPEG | 1200×800 | 3:2 | Optional | — | Phase 2
Local | Our Regions | West Coast card photo | Region-flavored action shot | JPEG | 1200×800 | 3:2 | Optional | — | Phase 2
Destinations | Hero | Hero background | Destination property hero — Cooperstown or Ripken-style wide shot | JPEG | 2400×1600 min | 3:2 | Placeholder | photo-dugout.png | Launch | Should signal 'weeklong trip' — bigger venue, families.
Destinations | Properties grid | Cooperstown All Star Village | Property identifying shot | JPEG | 1200×900 | 4:3 | Placeholder | photo-dugout.png | Launch
Destinations | Properties grid | Rocker B Ranch | Property identifying shot — Byrd Family Field or ranch | JPEG | 1200×900 | 4:3 | Placeholder | photo-flags.png | Launch
Destinations | Properties grid | Ripken Experience Aberdeen | Property identifying shot | JPEG | 1200×900 | 4:3 | Placeholder | photo-celebrate.png | Launch
Destinations | Properties grid | Ripken Experience Myrtle Beach | Property identifying shot — coastal feel | JPEG | 1200×900 | 4:3 | Placeholder | photo-running.png | Launch
Destinations | Properties grid | Ripken Experience Pigeon Forge | Property identifying shot — Smoky Mountains | JPEG | 1200×900 | 4:3 | Placeholder | photo-batter.png | Launch
Destinations | Properties grid | Sports Force Parks Cedar Point | Property identifying shot — theme-park backdrop | JPEG | 1200×900 | 4:3 | Placeholder | photo-field.png | Launch
Ripken | Hero | Hero background | Ripken-branded action — replica MLB field, walk-up music context | JPEG | 2400×1600 min | 3:2 | Placeholder | photo-celebrate.png | Launch | Should evoke the Big League Experience.
Ripken | The Ripken Experience | Aberdeen card photo | Aberdeen field — Cal Sr. Park or Cal's hometown context | JPEG | 1200×900 | 4:3 | Placeholder | photo-celebrate.png | Launch
Ripken | The Ripken Experience | Myrtle Beach card photo | Myrtle Beach property — beach-adjacent or MLB-replica field | JPEG | 1200×900 | 4:3 | Placeholder | photo-running.png | Launch
Ripken | The Ripken Experience | Pigeon Forge card photo | Pigeon Forge field — Smoky Mountain backdrop | JPEG | 1200×900 | 4:3 | Placeholder | photo-batter.png | Launch
Ripken | Pinnacle moment (Nationals) | Nationals feature image | Cooperstown championship moment — bracket, trophy, or 12U action | JPEG | 1600×1200 | 4:3 | Placeholder | photo-batter.png | Launch | Renders large in the Pinnacle moment section.
Training | Hero | Hero background | Camp / showcase context — players being evaluated, instructor visible | JPEG | 2400×1600 min | 3:2 | Placeholder | photo-pitcher.png | Launch | Distinct from event imagery — more focused, instructional.
Training | Our Programs | Baseball Factory card | Player evaluation / camp action | JPEG | 1200×900 | 4:3 | Placeholder | photo-batter.png | Launch
Training | Our Programs | All-Ripken Games card | Showcase / all-star game moment | JPEG | 1200×900 | 4:3 | Placeholder | photo-celebrate.png | Launch
Training | Our Programs | Prospect Select card | 14U–16U showcase action — middle-school-aged players | JPEG | 1200×900 | 4:3 | Placeholder | photo-pitcher.png | Launch
Training | Our Programs | Spring Training card | Preseason camp — week one of the season | JPEG | 1200×900 | 4:3 | Placeholder | photo-field.png | Launch
About | Hero | Hero background | Brand-defining wide shot — could mirror the Home hero or be distinct | JPEG | 2400×1600 min | 3:2 | Placeholder | hero.png | Launch | Sets the tone for the company narrative.
About | Our Story | Our Story photo | Side-by-side feature image — historical or signature property shot | JPEG | 1600×1200 | 4:3 | Placeholder | photo-dugout.png | Launch | Renders next to the founding-story copy.
About | Leadership | CEO headshot | Professional headshot — neutral background, shoulders-up | JPEG | 800×800 | 1:1 | Needed | [ Name ] placeholder | Launch (BLOCKER) | Real name + photo required before launch.
About | Leadership | President headshot | Professional headshot | JPEG | 800×800 | 1:1 | Needed | [ Name ] placeholder | Launch (BLOCKER) | Real name + photo required before launch.
About | Leadership | COO headshot | Professional headshot | JPEG | 800×800 | 1:1 | Needed | [ Name ] placeholder | Launch (BLOCKER) | Real name + photo required before launch.
About | Leadership | CMO headshot | Professional headshot | JPEG | 800×800 | 1:1 | Needed | [ Name ] placeholder | Launch (BLOCKER) | Real name + photo required before launch.

## Summary
Phase 1 Asset Summary
By Status | Count
Needed | 33
Placeholder | 20
Optional | 6
Have | 2
Have / Replace | 1
By Priority | Count
Launch | 49
Phase 2 | 6
Launch (BLOCKER) | 5
— | 2
By Page | Count
Home | 24
Local | 12
Destinations | 7
About | 6
Ripken | 5
Training | 5
Chrome | 3
TOTAL ASSETS | 62

## Specs reference
Dimensions & format reference
Usage | Recommended size | Notes
Hero background (page) | 2400×1600 (3:2) | Min 1920px wide. Compress to <400KB. Focal area lower-mid.
Feature card (carousel, founding star, story) | 1600×1200 (4:3) | Compress to <300KB.
Property / venue card | 1200×900 (4:3) or 1200×800 (3:2) | Compress to <200KB.
Voice card / square portrait | 1200×1200 (1:1) | Subject centered; works with circular masks too.
Leadership headshot | 800×800 (1:1) | Neutral background, shoulders-up, consistent lighting across the 4.
Partner logo | SVG preferred, or 400px tall PNG | Transparent background. Single-color or original brand color.
Favicon set | 16/32/180/512 + ICO | Generate from one 512×512 master.
Open Graph share image | 1200×630 (1.91:1) | Used by Facebook, LinkedIn, iMessage. Logo + key visual.
Background video (about teaser) | 1920×1080 H.264 MP4 | Muted, ≤15s loop, ≤5MB. Provide a JPEG poster too.